## Pre-filled Starter Sheet
Purpose Conveys the scope of various tasks that need to be coordinated to build and launch the product/feature | What is the task? Based on the purpose, select the appropriate from the drop-down | Who is the task owner? Does the following to finish task: 1. Schedule and run meetings 2. Gather feedback and share updates 3. Follow-up with stakeholders | Whose involvement is needed to accomplish the task ? Please select one from the drop-down list of your identified stakeholders | What is their role? Select the stakeholder's role from the drop-down. Note: 'Scrum Team' role is applicable to stakeholder 'Scrum Team' only | By when, does the task need to be completed? Select milestone keeping in mind nature of the task,downstream effects of delaying task
Evangelize internally | Setup PRD review meeting to receive feedback | Product Manager | Head of Product | Approver (Has the final say on a specific aspect of the project) | Set a target week
|  |  | Impacted Product Managers | Contributors (Consulted for their opinions or expertise to help with project decisions)
| Setup meeting to share MVP scope and walk-through design to gather feedback |  | Cross-functional Stakeholders | Contributors (Consulted for their opinions or expertise to help with project decisions)
| Setup meeting to kickoff project with the scrum team |  | Scrum Team | Scrum Team (Involved directly in product development efforts)
Involve legal and compliance | Get feedback on previously identified legal areas to update. e.g Terms of Use and Privacy Policy | Product Manager | Legal and Compliance | Contributors (Consulted for their opinions or expertise to help with project decisions) | Set a target week
| Setup meeting to review MVP scope and identify possible legal updates.e.g Terms of Use and Privacy Policy |  | Legal and Compliance | Contributors (Consulted for their opinions or expertise to help with project decisions) | Before project's sprint 0 starts
Incorporate stakeholders feedback | Discuss the prioritized feedback received from stakeholders to update scope and design | Product Manager | Product Designer | Scrum Team (Involved directly in product development efforts) | Before project's sprint 0 starts
Initiate and maintain feedback loop | Create a project-specific communication channel (in Slack etc) to share insights from customer meetings/usability tests/data analysis | Product Manager | Head of Product/Impacted Product Managers/Cross-functional stakeholders | Informed (No authority over the decisions and need to stay updated on the progress since it impacts t | Ongoing activity
Plan development work | Setup solution feasibility discussions to understand the work involved/identify inter-dependencies and potential risks | Product Manager | Scrum Team | Scrum Team (Involved directly in product development efforts) | Before project's sprint 0 starts
| Identify critical spike and engineering design work to complete prior to product/feature development | Engineering Lead
Manage product/feature testing | Share and review the project's test strategy | QA | Scrum Team | Scrum Team (Involved directly in product development efforts) | Before project's sprint 0 starts
Setup analytics tracking | Review analytics tracking requirements | Data Analyst | Scrum Team | Scrum Team (Involved directly in product development efforts) | Before project's sprint 0 starts
Prepare for every sprint | Create tickets for each sprint based on the test strategy | QA | Scrum Team | Scrum Team (Involved directly in product development efforts) | Before each sprint starts
| Create tickets for each sprint based on the analytics tracking requirements | Data Analyst
| Finalize user-stories and design to add for each sprint | Product Manager
Coordinate product/feature launch | Discuss launch plan and targeted timelines to align with development cycle | Product Marketing | Product Manager | Approver (Has the final say on a specific aspect of the project) | Before project's sprint 0 starts
| Identify the support material that needs to be prepared and targeted timelines to align with development cycle | Customer Service | Product Manager | Contributors (Consulted for their opinions or expertise to help with project decisions) | Before project's sprint 0 starts
Communicate project progress | Share project's progress and highlight any risks (setup recurring meeting/send email/ share via team's channel e.g Slack) | Product Manager | Head of Product/Impacted Product Managers/Cross-functional stakeholders | Informed (No authority over the decisions and need to stay updated on the progress since it impacts t | Before each sprint starts
Receive product/feature sign-off | Setup meeting to demo the feature and conduct end-to-end feature testing to identify bugs and receive feedback | Product Manager | Head of Product | Approver (Has the final say on a specific aspect of the project) | Before each sprint starts
|  |  | Impacted Product Managers | Contributors (Consulted for their opinions or expertise to help with project decisions)
|  |  | Cross-functional Stakeholders | Contributors (Consulted for their opinions or expertise to help with project decisions)
Note on A20: these should be 11a, 11b, 11c -Unknown Hi +michele.cavaioni@udacity.com It is usually in the same meeting or two different meetings, but I have kept as one over here. updated the numbering -Yuva Sharanyah Murugan

## Sheet2 (hidden)
Create a project-specific communication channel (in Slack etc) to share insights from customer meetings/usability tests/data analysis
Create tickets for each sprint based on the test strategy
Discuss launch plan and targeted timelines to align with development cycle
Discuss the prioritized feedback received from stakeholders to update scope and design
Finalize user-stories and design to add for each sprint
Get feedback on previously identified legal areas to update. e.g Terms of Use and Privacy Policy
Identify critical spike and engineering design work to complete prior to product/feature development
Identify the support material that needs to be prepared and targeted timelines to align with development cycle
Review analytics tracking requirements
Setup meeting to share MVP scope and walk-through design to gather feedback
Setup meeting to review MVP scope and identify possible legal updates.e.g Terms of Use and Privacy Policy
Share project's progress and highlight any risks (setup recurring meeting/send email/ share via team's channel e.g Slack)

## Help Information
Stakeholders identified for the project
Head of Product
Impacted Product Managers (Your product/feature impact the product/feature they mange directly or indirectly)
Cross-functional Stakeholders (Representation from these areas: Customer Service, Marketing (includes Product Marketing) and Operations )
Scrum Team (Mentioned here)
Legal and Compliance
Customer Service